## optimized backend ops
Update required (yellow color - Update required) | comments
Links - Oracle Link take user to MS Site no Oracle Fusion - P1 – Please provide link for Oracle Fusion as It was not provided to us! | done
Must change to About Us to About US | done
Get in Touch Form All enquiries are going to General Enquiries not the teams for the service stated | done
Page - Team Member salute has boiler plate content - P1 – Didn’t understand what this means? - Boiler Plate Text:- · Lorem Ipsum dolor sit amet. · Consectetur adipiscing elit. · Sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. · Ut enim ad minim veniam. Excepteur sint occaecat cupidatat. | it's dummy data, it can be updated if appropriate content is delivered
Forms Forms - Issues, confusing for users to use, forms sent to wrong team in ME - P1 – This is going to the groups as provided to us. | please do mention the confusing forms
Content Approval by admin if required | need more clarification
Site Map must be created | need more clarification
Activate Search button | need more clarification
No version control | need more clarification
View option before publishing | need more clarification
Issue still impacting go-live (red color - Issue still impacting go-live)
Feedback Form: Must change first field- Type of Enquiry in the drop down menu to Select, Replace Type of Enquiry with Select | done
Complaints and Feedback/ Form Under Emirate—> replace the word city in the question with Emirate. It should become: In which Emirates did the incident take place? | done
Links not working. Get 404 page not found. | please do mention the links that are not working
Clicking on the Logo returns to WebSite Home Page | please do mention where it should be redirected or whether needed any redirection
If you then click on the Employee portal page you get to a broken Portal Admin Page | please do check & if not correct needs more clarification
Feedback form Duplicate Call References on submission of Forms | need more clarification
References not sequential and looks like there is a different counter for complaints and compliments but both are sent with the same prefix so it is possible to have duplicate IDs for two different cases. | need more clarification
Feedback Form SMS Missing the ReferenceID | please do check again & confirm
SMS Does not Mention National Ambulance | please do check again & confirm
Additional Comments for Review (purple color - Additional Comments for Review)
Admin Portal - Issues not Usable in current status | need more clarification
Admin account - No way to change password | please do check & if not correct needs more clarification
User Accounts - No way to change passwords for users | please do check under Employee management after logging in as Admin & confirm.